## Gantt Chart (weeks)
Tasks | Activity | Start Date | End Date | 2024
|  |  |  | May |  |  |  |  | June |  |  |  | July
|  |  |  | 01/May - 07/May | 08/May - 14/May | 15/May - 21/May | 22/May - 28/May | 29/May - 04/Jun | 05/Jun - 11/Jun | 12/Jun - 18/Jun | 19/Jun - 25/Jun | 26/Jun - 02/Jul | 03/Jul - 09/Jul | 10/Jul - 16/Jul | 17/Jul - 23/Jul
Task 1 | Requirements Gathering | 01-May-2024 | 14-May-2024
1.1 | Initial Meeting | 01-May-2024 | 07-May-2024
1.2 | Stakeholder Interviews | 01-May-2024 | 07-May-2024
1.3 | Requirements Documentation | 01-May-2024 | 14-May-2024
Task 2 | Design | 15-May-2024 | 28-May-2024
2.1 | Design | 15-May-2024 | 21-May-2024
2.2 | Database Schema Design | 15-May-2024 | 28-May-2024
2.3 | UI/UX Design | 22-May-2024 | 28-May-2024
Task 3 | Development | 29-May-2024 | 18-Jun-2024
3.1 | Frontend Development | 29-May-2024 | 04-Jun-2024
3.2 | Backend Development | 05-Jun-2024 | 18-Jun-2024
3.3 | Integration | 12-Jun-2024 | 18-Jun-2024
Task 4 | Testing | 19-Jun-2024 | 02-Jul-2024
4.1 | Unit Testing | 19-Jun-2024 | 25-Jun-2024
4.2 | Integration Testing | 19-Jun-2024 | 02-Jul-2024
4.3 | User Acceptance Testing | 26-Jun-2024 | 02-Jul-2024
Task 5 | Deployment | 03-Jul-2024 | 09-Jul-2024
5.1 | Prepare Deployment Environment | 03-Jul-2024 | 09-Jul-2024
5.2 | Deployment | 03-Jul-2024 | 09-Jul-2024
5.3 | Post-Deployment Verification | 03-Jul-2024 | 09-Jul-2024
Task 6 | Maintenance | 10-Jul-2024 | 23-Jul-2024
6.1 | Bug Fixing | 10-Jul-2024 | 16-Jul-2024
6.2 | Performance Tuning | 10-Jul-2024 | 16-Jul-2024
6.3 | User Training | 10-Jul-2024 | 23-Jul-2024

## Gantt Chart (months)
Tasks | Activity | Start Date | End Date | 2024
|  |  |  | May |  |  |  |  | June |  |  |  | July
|  |  |  | 01/May - 07/May | 08/May - 14/May | 15/May - 21/May | 22/May - 28/May | 29/May - 04/Jun | 05/Jun - 11/Jun | 12/Jun - 18/Jun | 19/Jun - 25/Jun | 26/Jun - 02/Jul | 03/Jul - 09/Jul | 10/Jul - 16/Jul | 17/Jul - 23/Jul
Task 1 | Requirements Gathering | 01-May-2024 | 14-May-2024
Task 2 | Design | 15-May-2024 | 28-May-2024
Task 3 | Development | 29-May-2024 | 18-Jun-2024
Task 4 | Testing | 19-Jun-2024 | 02-Jul-2024
Task 5 | Deployment | 03-Jul-2024 | 09-Jul-2024
Task 6 | Maintenance | 10-Jul-2024 | 23-Jul-2024

## Project Schedule
Tasks | Activity | Start Date | End Date | Status
Task 1 | Requirements Gathering | 01-May-2024 | 14-May-2024 | At Risk
1.1 | Initial Meeting | 01-May-2024 | 07-May-2024 | Delayed
1.2 | Stakeholder Interviews | 01-May-2024 | 07-May-2024 | Delayed
1.3 | Requirements Documentation | 01-May-2024 | 14-May-2024 | Delayed
Task 2 | Design | 15-May-2024 | 28-May-2024 | Ongoing
2.1 | Design | 15-May-2024 | 21-May-2024 | Ongoing
2.2 | Database Schema Design | 15-May-2024 | 28-May-2024 | Ongoing
2.3 | UI/UX Design | 22-May-2024 | 28-May-2024 | Ongoing
Task 3 | Development | 29-May-2024 | 18-Jun-2024 | Ongoing
3.1 | Frontend Development | 29-May-2024 | 04-Jun-2024 | Ongoing
3.2 | Backend Development | 05-Jun-2024 | 18-Jun-2024 | Ongoing
3.3 | Integration | 12-Jun-2024 | 18-Jun-2024 | Ongoing
Task 4 | Testing | 19-Jun-2024 | 02-Jul-2024 | Ongoing
4.1 | Unit Testing | 19-Jun-2024 | 25-Jun-2024 | Ongoing
4.2 | Integration Testing | 19-Jun-2024 | 02-Jul-2024 | Ongoing
4.3 | User Acceptance Testing | 26-Jun-2024 | 02-Jul-2024 | Ongoing
Task 5 | Deployment | 03-Jul-2024 | 09-Jul-2024 | Ongoing
5.1 | Prepare Deployment Environment | 03-Jul-2024 | 09-Jul-2024 | Ongoing
5.2 | Deployment | 03-Jul-2024 | 09-Jul-2024 | Ongoing
5.3 | Post-Deployment Verification | 03-Jul-2024 | 09-Jul-2024 | Ongoing
Task 6 | Maintenance | 10-Jul-2024 | 23-Jul-2024 | Ongoing
6.1 | Bug Fixing | 10-Jul-2024 | 16-Jul-2024 | Ongoing
6.2 | Performance Tuning | 10-Jul-2024 | 16-Jul-2024 | Ongoing
6.3 | User Training | 10-Jul-2024 | 23-Jul-2024 | Ongoing