## Gantt Chart (weeks)
Tasks | Activity | Start Date | End Date | Priority | 2024
[5 empty] | April |  |  | May |  |  |  |  | June
[5 empty] | 10/Apr - 16/Apr | 17/Apr - 23/Apr | 24/Apr - 30/Apr | 01/May - 07/May | 08/May - 14/May | 15/May - 21/May | 22/May - 28/May | 29/May - 04/Jun | 05/Jun - 11/Jun | 12/Jun - 18/Jun | 19/Jun - 25/Jun | 26/Jun - 02/Jul
Task 1 | Requirements Gathering | 10-Apr-2024 | 23-Apr-2024 | Low
1.1 | Initial Meeting | 10-Apr-2024 | 16-Apr-2024 | Low
1.2 | Stakeholder Interviews | 10-Apr-2024 | 16-Apr-2024 | Low
1.3 | Requirements Documentation | 10-Apr-2024 | 23-Apr-2024 | Low
Task 2 | Design | 24-Apr-2024 | 07-May-2024 | Low
2.1 | System Architecture Design | 24-Apr-2024 | 30-Apr-2024 | Low
2.2 | Database Schema Design | 24-Apr-2024 | 07-May-2024 | Low
2.3 | UI/UX Design | 01-May-2024 | 07-May-2024 | Low
Task 3 | Development | 08-May-2024 | 28-May-2024 | Low
3.1 | Frontend Development | 08-May-2024 | 14-May-2024 | Low
3.2 | Backend Development | 15-May-2024 | 28-May-2024 | Low
3.3 | Integration | 22-May-2024 | 28-May-2024 | Low
Task 4 | Testing | 29-May-2024 | 11-Jun-2024 | Low
4.1 | Unit Testing | 29-May-2024 | 04-Jun-2024 | Low
4.2 | Integration Testing | 29-May-2024 | 11-Jun-2024 | Low
4.3 | User Acceptance Testing | 05-Jun-2024 | 11-Jun-2024 | Low
Task 5 | Deployment | 12-Jun-2024 | 18-Jun-2024 | Low
5.1 | Prepare Deployment Environment | 12-Jun-2024 | 18-Jun-2024 | Low
5.2 | Deployment | 12-Jun-2024 | 18-Jun-2024 | Low
5.3 | Post-Deployment Verification | 12-Jun-2024 | 18-Jun-2024 | Low
Task 6 | Maintenance | 19-Jun-2024 | 02-Jul-2024 | Low
6.1 | Bug Fixing | 19-Jun-2024 | 25-Jun-2024 | Low
6.2 | Performance Tuning | 19-Jun-2024 | 25-Jun-2024 | Low
6.3 | User Training | 19-Jun-2024 | 02-Jul-2024 | Low

## Gantt Chart (months)
Tasks | Activity | Start Date | End Date | Priority | 2024
[5 empty] | April |  |  | May |  |  |  |  | June
[5 empty] | 10/Apr - 16/Apr | 17/Apr - 23/Apr | 24/Apr - 30/Apr | 01/May - 07/May | 08/May - 14/May | 15/May - 21/May | 22/May - 28/May | 29/May - 04/Jun | 05/Jun - 11/Jun | 12/Jun - 18/Jun | 19/Jun - 25/Jun | 26/Jun - 02/Jul
Task 1 | Requirements Gathering | 10-Apr-2024 | 23-Apr-2024 | Low
Task 2 | Design | 24-Apr-2024 | 07-May-2024 | Low
Task 3 | Development | 08-May-2024 | 28-May-2024 | Low
Task 4 | Testing | 29-May-2024 | 11-Jun-2024 | Low
Task 5 | Deployment | 12-Jun-2024 | 18-Jun-2024 | Low
Task 6 | Maintenance | 19-Jun-2024 | 02-Jul-2024 | Low

## Project Schedule
Tasks | Activity | Start Date | End Date | Status | Complete
Task 1 | Requirements Gathering | 10-Apr-2024 | 23-Apr-2024 | Delayed | 0%
1.1 | Initial Meeting | 10-Apr-2024 | 16-Apr-2024 | Delayed | 0%
1.2 | Stakeholder Interviews | 10-Apr-2024 | 16-Apr-2024 | Delayed | 0%
1.3 | Requirements Documentation | 10-Apr-2024 | 23-Apr-2024 | Delayed | 0%
Task 2 | Design | 24-Apr-2024 | 07-May-2024 | Delayed | 0%
2.1 | System Architecture Design | 24-Apr-2024 | 30-Apr-2024 | Delayed | 0%
2.2 | Database Schema Design | 24-Apr-2024 | 07-May-2024 | Delayed | 0%
2.3 | UI/UX Design | 01-May-2024 | 07-May-2024 | Delayed | 0%
Task 3 | Development | 08-May-2024 | 28-May-2024 | At Risk | 0%
3.1 | Frontend Development | 08-May-2024 | 14-May-2024 | Delayed | 0%
3.2 | Backend Development | 15-May-2024 | 28-May-2024 | Ongoing | 0%
3.3 | Integration | 22-May-2024 | 28-May-2024 | Ongoing | 0%
Task 4 | Testing | 29-May-2024 | 11-Jun-2024 | Ongoing | 0%
4.1 | Unit Testing | 29-May-2024 | 04-Jun-2024 | Ongoing | 0%
4.2 | Integration Testing | 29-May-2024 | 11-Jun-2024 | Ongoing | 0%
4.3 | User Acceptance Testing | 05-Jun-2024 | 11-Jun-2024 | Ongoing | 0%
Task 5 | Deployment | 12-Jun-2024 | 18-Jun-2024 | Ongoing | 0%
5.1 | Prepare Deployment Environment | 12-Jun-2024 | 18-Jun-2024 | Ongoing | 0%
5.2 | Deployment | 12-Jun-2024 | 18-Jun-2024 | Ongoing | 0%
5.3 | Post-Deployment Verification | 12-Jun-2024 | 18-Jun-2024 | Ongoing | 0%
Task 6 | Maintenance | 19-Jun-2024 | 02-Jul-2024 | Ongoing | 0%
6.1 | Bug Fixing | 19-Jun-2024 | 25-Jun-2024 | Ongoing | 0%
6.2 | Performance Tuning | 19-Jun-2024 | 25-Jun-2024 | Ongoing | 0%
6.3 | User Training | 19-Jun-2024 | 02-Jul-2024 | Ongoing | 0%

## RACI Table
Tasks | Activity | Start Date | End Date | Product Owner | Business Analyst | Financial Lead | Design Director | CRM Lead | Head of CRM | Senior Stakeholders* | Senior Stakeholders** | AGENCY
Task 1 | Requirements Gathering | 10-Apr-2024 | 23-Apr-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
1.1 | Initial Meeting | 10-Apr-2024 | 16-Apr-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
1.2 | Stakeholder Interviews | 10-Apr-2024 | 16-Apr-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
1.3 | Requirements Documentation | 10-Apr-2024 | 23-Apr-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
Task 2 | Design | 24-Apr-2024 | 07-May-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
2.1 | System Architecture Design | 24-Apr-2024 | 30-Apr-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
2.2 | Database Schema Design | 24-Apr-2024 | 07-May-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
2.3 | UI/UX Design | 01-May-2024 | 07-May-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
Task 3 | Development | 08-May-2024 | 28-May-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
3.1 | Frontend Development | 08-May-2024 | 14-May-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
3.2 | Backend Development | 15-May-2024 | 28-May-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
3.3 | Integration | 22-May-2024 | 28-May-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
Task 4 | Testing | 29-May-2024 | 11-Jun-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
4.1 | Unit Testing | 29-May-2024 | 04-Jun-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
4.2 | Integration Testing | 29-May-2024 | 11-Jun-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
4.3 | User Acceptance Testing | 05-Jun-2024 | 11-Jun-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
Task 5 | Deployment | 12-Jun-2024 | 18-Jun-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
5.1 | Prepare Deployment Environment | 12-Jun-2024 | 18-Jun-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
5.2 | Deployment | 12-Jun-2024 | 18-Jun-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
5.3 | Post-Deployment Verification | 12-Jun-2024 | 18-Jun-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
Task 6 | Maintenance | 19-Jun-2024 | 02-Jul-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
6.1 | Bug Fixing | 19-Jun-2024 | 25-Jun-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
6.2 | Performance Tuning | 19-Jun-2024 | 25-Jun-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
6.3 | User Training | 19-Jun-2024 | 02-Jul-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible