## Gantt Chart (weeks)
Tasks | Activity | Start Date | End Date | Priority | 2024
[5 empty] | April |  |  | May |  |  |  |  | June
[5 empty] | 10/Apr - 16/Apr | 17/Apr - 23/Apr | 24/Apr - 30/Apr | 01/May - 07/May | 08/May - 14/May | 15/May - 21/May | 22/May - 28/May | 29/May - 04/Jun | 05/Jun - 11/Jun
Task 1 | M1 | 10-Apr-2024 | 30-Apr-2024 | High
1.1 | A | 10-Apr-2024 | 16-Apr-2024 | Low
1.2 | B | 17-Apr-2024 | 23-Apr-2024 | Medium
1.3 | C | 24-Apr-2024 | 30-Apr-2024 | High
Task 2 | M2 | 01-May-2024 | 21-May-2024 | Low
2.1 | D | 01-May-2024 | 07-May-2024 | Low
2.2 | E | 08-May-2024 | 14-May-2024 | Low
2.3 | F | 15-May-2024 | 21-May-2024 | Low
Task 3 | M3 | 22-May-2024 | 11-Jun-2024 | High
3.1 | G | 22-May-2024 | 28-May-2024 | Low
3.2 | H | 29-May-2024 | 04-Jun-2024 | Medium
3.3 | I | 05-Jun-2024 | 11-Jun-2024 | High

## Gantt Chart (months)
Tasks | Activity | Start Date | End Date | Priority | 2024
[5 empty] | April |  |  | May |  |  |  |  | June
[5 empty] | 10/Apr - 16/Apr | 17/Apr - 23/Apr | 24/Apr - 30/Apr | 01/May - 07/May | 08/May - 14/May | 15/May - 21/May | 22/May - 28/May | 29/May - 04/Jun | 05/Jun - 11/Jun
Task 1 | M1 | 10-Apr-2024 | 30-Apr-2024 | High
Task 2 | M2 | 01-May-2024 | 21-May-2024 | Low
Task 3 | M3 | 22-May-2024 | 11-Jun-2024 | High

## Project Schedule
Tasks | Activity | Start Date | End Date | Status | Complete
Task 1 | M1 | 10-Apr-2024 | 30-Apr-2024 | Delayed | 0%
1.1 | A | 10-Apr-2024 | 16-Apr-2024 | Delayed | 0%
1.2 | B | 17-Apr-2024 | 23-Apr-2024 | Delayed | 0%
1.3 | C | 24-Apr-2024 | 30-Apr-2024 | Delayed | 0%
Task 2 | M2 | 01-May-2024 | 21-May-2024 | Delayed | 0%
2.1 | D | 01-May-2024 | 07-May-2024 | Delayed | 0%
2.2 | E | 08-May-2024 | 14-May-2024 | Delayed | 0%
2.3 | F | 15-May-2024 | 21-May-2024 | Delayed | 0%
Task 3 | M3 | 22-May-2024 | 11-Jun-2024 | Ongoing | 0%
3.1 | G | 22-May-2024 | 28-May-2024 | Ongoing | 0%
3.2 | H | 29-May-2024 | 04-Jun-2024 | Ongoing | 0%
3.3 | I | 05-Jun-2024 | 11-Jun-2024 | Ongoing | 0%

## RACI Table
Tasks | Activity | Start Date | End Date | Product Owner | Business Analyst | Financial Lead | Design Director | CRM Lead | Head of CRM | Senior Stakeholders* | Senior Stakeholders** | AGENCY
Task 1 | M1 | 10-Apr-2024 | 30-Apr-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
1.1 | A | 10-Apr-2024 | 16-Apr-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
1.2 | B | 17-Apr-2024 | 23-Apr-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
1.3 | C | 24-Apr-2024 | 30-Apr-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
Task 2 | M2 | 01-May-2024 | 21-May-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
2.1 | D | 01-May-2024 | 07-May-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
2.2 | E | 08-May-2024 | 14-May-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
2.3 | F | 15-May-2024 | 21-May-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
Task 3 | M3 | 22-May-2024 | 11-Jun-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
3.1 | G | 22-May-2024 | 28-May-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
3.2 | H | 29-May-2024 | 04-Jun-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
3.3 | I | 05-Jun-2024 | 11-Jun-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible