## Gantt Chart (weeks)
Tasks | Activity | Start Date | End Date | Priority | 2024
[5 empty] | May |  |  |  | June |  |  |  | July
[5 empty] | 10/May - 16/May | 17/May - 23/May | 24/May - 30/May | 31/May - 06/Jun | 07/Jun - 13/Jun | 14/Jun - 20/Jun | 21/Jun - 27/Jun | 28/Jun - 04/Jul | 05/Jul - 11/Jul | 12/Jul - 18/Jul | 19/Jul - 25/Jul | 26/Jul - 01/Aug
Task 1 | Requirements Gathering | 10-May-2024 | 23-May-2024 | Medium
1.1 | Initial Meeting | 10-May-2024 | 16-May-2024 | Medium
1.2 | Stakeholder Interviews | 10-May-2024 | 16-May-2024 | Low
1.3 | Requirements Documentation | 10-May-2024 | 23-May-2024 | Low
Task 2 | Design | 24-May-2024 | 06-Jun-2024 | Low
2.1 | System Architecture Design | 24-May-2024 | 30-May-2024 | Low
2.2 | Database Schema Design | 24-May-2024 | 06-Jun-2024 | Low
2.3 | UI/UX Design | 31-May-2024 | 06-Jun-2024 | Low
Task 3 | Development | 07-Jun-2024 | 27-Jun-2024 | Medium
3.1 | Frontend Development | 07-Jun-2024 | 13-Jun-2024 | Medium
3.2 | Backend Development | 14-Jun-2024 | 27-Jun-2024 | Medium
3.3 | Integration | 21-Jun-2024 | 27-Jun-2024 | Medium
Task 4 | Testing | 28-Jun-2024 | 11-Jul-2024 | High
4.1 | Unit Testing | 28-Jun-2024 | 04-Jul-2024 | High
4.2 | Integration Testing | 28-Jun-2024 | 11-Jul-2024 | Medium
4.3 | User Acceptance Testing | 05-Jul-2024 | 11-Jul-2024 | Low
Task 5 | Deployment | 12-Jul-2024 | 18-Jul-2024 | Medium
5.1 | Prepare Deployment Environment | 12-Jul-2024 | 18-Jul-2024 | Medium
5.2 | Deployment | 12-Jul-2024 | 18-Jul-2024 | Low
5.3 | Post-Deployment Verification | 12-Jul-2024 | 18-Jul-2024 | Low
Task 6 | Maintenance | 19-Jul-2024 | 01-Aug-2024 | High
6.1 | Bug Fixing | 19-Jul-2024 | 25-Jul-2024 | High
6.2 | Performance Tuning | 19-Jul-2024 | 25-Jul-2024 | High
6.3 | User Training | 19-Jul-2024 | 01-Aug-2024 | Low

## Gantt Chart (months)
Tasks | Activity | Start Date | End Date | Priority | 2024
[5 empty] | May |  |  |  | June |  |  |  | July
[5 empty] | 10/May - 16/May | 17/May - 23/May | 24/May - 30/May | 31/May - 06/Jun | 07/Jun - 13/Jun | 14/Jun - 20/Jun | 21/Jun - 27/Jun | 28/Jun - 04/Jul | 05/Jul - 11/Jul | 12/Jul - 18/Jul | 19/Jul - 25/Jul | 26/Jul - 01/Aug
Task 1 | Requirements Gathering | 10-May-2024 | 23-May-2024 | Medium
Task 2 | Design | 24-May-2024 | 06-Jun-2024 | Low
Task 3 | Development | 07-Jun-2024 | 27-Jun-2024 | Medium
Task 4 | Testing | 28-Jun-2024 | 11-Jul-2024 | High
Task 5 | Deployment | 12-Jul-2024 | 18-Jul-2024 | Medium
Task 6 | Maintenance | 19-Jul-2024 | 01-Aug-2024 | High

## Project Schedule
Tasks | Activity | Start Date | End Date | Status | Complete
Task 1 | Requirements Gathering | 10-May-2024 | 23-May-2024 | Delayed | 0%
1.1 | Initial Meeting | 10-May-2024 | 16-May-2024 | Delayed | 0%
1.2 | Stakeholder Interviews | 10-May-2024 | 16-May-2024 | Delayed | 0%
1.3 | Requirements Documentation | 10-May-2024 | 23-May-2024 | Delayed | 0%
Task 2 | Design | 24-May-2024 | 06-Jun-2024 | Ongoing | 0%
2.1 | System Architecture Design | 24-May-2024 | 30-May-2024 | Ongoing | 0%
2.2 | Database Schema Design | 24-May-2024 | 06-Jun-2024 | Ongoing | 0%
2.3 | UI/UX Design | 31-May-2024 | 06-Jun-2024 | Ongoing | 0%
Task 3 | Development | 07-Jun-2024 | 27-Jun-2024 | Ongoing | 0%
3.1 | Frontend Development | 07-Jun-2024 | 13-Jun-2024 | Ongoing | 0%
3.2 | Backend Development | 14-Jun-2024 | 27-Jun-2024 | Ongoing | 0%
3.3 | Integration | 21-Jun-2024 | 27-Jun-2024 | Ongoing | 0%
Task 4 | Testing | 28-Jun-2024 | 11-Jul-2024 | Ongoing | 0%
4.1 | Unit Testing | 28-Jun-2024 | 04-Jul-2024 | Ongoing | 0%
4.2 | Integration Testing | 28-Jun-2024 | 11-Jul-2024 | Ongoing | 0%
4.3 | User Acceptance Testing | 05-Jul-2024 | 11-Jul-2024 | Ongoing | 0%
Task 5 | Deployment | 12-Jul-2024 | 18-Jul-2024 | Ongoing | 0%
5.1 | Prepare Deployment Environment | 12-Jul-2024 | 18-Jul-2024 | Ongoing | 0%
5.2 | Deployment | 12-Jul-2024 | 18-Jul-2024 | Ongoing | 0%
5.3 | Post-Deployment Verification | 12-Jul-2024 | 18-Jul-2024 | Ongoing | 0%
Task 6 | Maintenance | 19-Jul-2024 | 01-Aug-2024 | Ongoing | 0%
6.1 | Bug Fixing | 19-Jul-2024 | 25-Jul-2024 | Ongoing | 0%
6.2 | Performance Tuning | 19-Jul-2024 | 25-Jul-2024 | Ongoing | 0%
6.3 | User Training | 19-Jul-2024 | 01-Aug-2024 | Ongoing | 0%

## RACI Table
Tasks | Activity | Start Date | End Date | John Smith | Jane Doe | Emily Davis | Michael Brown | Olivia Johnson | Liam Williams | Sophia Martinez | William Garcia | Ava Lee
Task 1 | Requirements Gathering | 10-May-2024 | 23-May-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
1.1 | Initial Meeting | 10-May-2024 | 16-May-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
1.2 | Stakeholder Interviews | 10-May-2024 | 16-May-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
1.3 | Requirements Documentation | 10-May-2024 | 23-May-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
Task 2 | Design | 24-May-2024 | 06-Jun-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
2.1 | System Architecture Design | 24-May-2024 | 30-May-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
2.2 | Database Schema Design | 24-May-2024 | 06-Jun-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
2.3 | UI/UX Design | 31-May-2024 | 06-Jun-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
Task 3 | Development | 07-Jun-2024 | 27-Jun-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
3.1 | Frontend Development | 07-Jun-2024 | 13-Jun-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
3.2 | Backend Development | 14-Jun-2024 | 27-Jun-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
3.3 | Integration | 21-Jun-2024 | 27-Jun-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
Task 4 | Testing | 28-Jun-2024 | 11-Jul-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
4.1 | Unit Testing | 28-Jun-2024 | 04-Jul-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
4.2 | Integration Testing | 28-Jun-2024 | 11-Jul-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
4.3 | User Acceptance Testing | 05-Jul-2024 | 11-Jul-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
Task 5 | Deployment | 12-Jul-2024 | 18-Jul-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
5.1 | Prepare Deployment Environment | 12-Jul-2024 | 18-Jul-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
5.2 | Deployment | 12-Jul-2024 | 18-Jul-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
5.3 | Post-Deployment Verification | 12-Jul-2024 | 18-Jul-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
Task 6 | Maintenance | 19-Jul-2024 | 01-Aug-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
6.1 | Bug Fixing | 19-Jul-2024 | 25-Jul-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
6.2 | Performance Tuning | 19-Jul-2024 | 25-Jul-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible
6.3 | User Training | 19-Jul-2024 | 01-Aug-2024 | Accountable | Informed | Consulted | Informed | Consulted | Informed | Consulted | Informed | Responsible