## Gantt Chart (weeks)
Tasks | Activity | Start Date | End Date | 2024
|  |  |  | May |  | June |  |  |  | July |  |  |  |  | August
|  |  |  | 20/May - 26/May | 27/May - 02/Jun | 03/Jun - 09/Jun | 10/Jun - 16/Jun | 17/Jun - 23/Jun | 24/Jun - 30/Jun | 01/Jul - 07/Jul | 08/Jul - 14/Jul | 15/Jul - 21/Jul | 22/Jul - 28/Jul | 29/Jul - 04/Aug | 05/Aug - 11/Aug
Task 1 | Requirements Gathering | 20-May | 02-Jun
1.1 | Initial Meeting | 20-May | 26-May
1.2 | Stakeholder Interviews | 20-May | 26-May
1.3 | Requirements Documentation | 20-May | 02-Jun
Task 2 | Design | 03-Jun | 16-Jun
2.1 | System Architecture Design | 03-Jun | 09-Jun
2.2 | Database Schema Design | 03-Jun | 16-Jun
2.3 | UI/UX Design | 10-Jun | 16-Jun
Task 3 | Development | 17-Jun | 07-Jul
3.1 | Frontend Development | 17-Jun | 23-Jun
3.2 | Backend Development | 24-Jun | 07-Jul
3.3 | Integration | 01-Jul | 07-Jul
Task 4 | Testing | 08-Jul | 21-Jul
4.1 | Unit Testing | 08-Jul | 14-Jul
4.2 | Integration Testing | 08-Jul | 21-Jul
4.3 | User Acceptance Testing | 15-Jul | 21-Jul
Task 5 | Deployment | 22-Jul | 28-Jul
5.1 | Prepare Deployment Environment | 22-Jul | 28-Jul
5.2 | Deployment | 22-Jul | 28-Jul
5.3 | Post-Deployment Verification | 22-Jul | 28-Jul
Task 6 | Maintenance | 29-Jul | 11-Aug
6.1 | Bug Fixing | 29-Jul | 04-Aug
6.2 | Performance Tuning | 29-Jul | 04-Aug
6.3 | User Training | 29-Jul | 11-Aug

## Gantt Chart (months)
Tasks | Activity | Start Date | End Date | 2024
|  |  |  | May |  | June |  |  |  | July |  |  |  |  | August
|  |  |  | 20/May - 26/May | 27/May - 02/Jun | 03/Jun - 09/Jun | 10/Jun - 16/Jun | 17/Jun - 23/Jun | 24/Jun - 30/Jun | 01/Jul - 07/Jul | 08/Jul - 14/Jul | 15/Jul - 21/Jul | 22/Jul - 28/Jul | 29/Jul - 04/Aug | 05/Aug - 11/Aug
Task 1 | Requirements Gathering | 20-May | 02-Jun
Task 2 | Design | 03-Jun | 16-Jun
Task 3 | Development | 17-Jun | 07-Jul
Task 4 | Testing | 08-Jul | 21-Jul
Task 5 | Deployment | 22-Jul | 28-Jul
Task 6 | Maintenance | 29-Jul | 11-Aug